## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Rare Pyramid Bookstore Management System
| Organizations | CTU
| Project | Rare Pyramid Bookstore Management System
| Product Owner | Robert Campbell
| Scrum Master | Phillip Cook
| Development Team | Kalder Morgan and Regina Cleveland
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | Login Page | Allows customers or admin to login to the system(As a customer or admin I want to be able to log into the bookstore) | • Given a registered user, when valid credentials are entered, then the user is logged in and redirected to the dashboard • Given invalid credentials, when login is attempted, then an error message is displayed • Given a user, when accessing the system, then login is required before access is granted • Given an admin, when logged in, then admin-specific features are accessible | 1 | 2
2 | Inventory Browser | Allows customer to view availiable inventory(As a customer I want to have the ability to view product inventory) | • Given a customer, when they open the inventory page, then a list of available books is displayed • Given inventory exists, then each item shows title, price, and availability • Given no inventory, then a “no items available” message is shown | 1 | 1
3 | Inventory Update System | Allows administrators to update inventory, and automatically update inventory when a sale is made to reflect new inventory count(As an admin I would like for the inventory to update itself when needed and the ability update it manually also when needed) | • Given an admin, when they update inventory manually, then the system reflects the new quantity • Given a purchase occurs, when checkout completes, then inventory is reduced automatically • Given inventory reaches zero, then the item is marked as out of stock • Given invalid input (e.g., negative stock), then the system rejects the update | 4 | 1
4 | Cart System | Allows customers to add items to a "cart" to be purchased(As a customer I would like the ability to place items in a cart I can return to later) | • Given a customer, when they add an item, then it appears in the cart • Given items in cart, when the user leaves and returns, then the cart persists (session or account-based) • Given a cart item, when removed, then it no longer appears in the cart • Given duplicate items added, then quantity updates instead of duplicating entries | 2 | 2
5 | Order Processing(Customer) | Allows for order and payment processing once an order is placed by a customer(As a customer I would like the ability to have my payment and order processed) | • Given items in cart, when checkout is completed, then an order is created • Given valid payment, then the transaction is processed successfully • Given failed payment, then the order is not completed and user is notified • Given a completed order, then confirmation is displayed and/or emailed | 2 | 1
6 | Order Processing(Manufacturer) | Allows for orders to be placed by an admin to restock inventory(As an admin I would like the ability to order inventory from the manufactorer) | • Given an admin, when they place a restock order, then a purchase order is created • Given a restock order, when fulfilled, then inventory increases accordingly • Given invalid order data, then the system prevents submission | 3 | 1
7 | Sales Report Generation | Allows for admins to generate a sales report(As an admin I would like the ability to generate a sales report) | • Given an admin, when requesting a sales report, then the system generates a report • Given a date range, then the report reflects only that period • Given report generation, then totals (revenue, items sold) are included • Given report completion, then it can be viewed and/or downloaded | 3 | 2
8 | Inventory Report Generation | Allows for admins to generate an inventory report(As an admin I would like the ability to generate an inventory report) | • Given an admin, when generating a report, then all inventory items are listed • Given inventory levels, then quantities and stock status are included • Given report generation, then it reflects current system data | 4 | 2
9 | General Security | Ensure the software is using reasonable security such as encryption and authentication(As a product owner I would like to ensure that this software has reasonable security) | • Given user credentials, then they are stored securely (e.g., hashed passwords) • Given login activity, then authentication is required for protected actions • Given sensitive data, then it is transmitted securely (e.g., HTTPS) • Given multiple failed logins, then protection (e.g., lockout or throttling) is applied | 5 | 2
10 | Inventory Search Feature | Allows the ability to search the inventory as a customer(As a customer I would like the ability to search the inventory) | • Given a search query, when entered, then matching inventory items are displayed • Given no matches, then a “no results found” message appears • Given partial matches, then relevant results are returned • Given search results, then users can select items to view details | 5 | 1

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Bookstore Management System (BMS)
|  | Sprint # |  | 1
|  | Start date |  | 2026-05-05
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18
1.1 | 2,10 | Build inventory browsing UI + search functionality | Regina Cleveland | 4 | 2026-05-10: 2; 2026-05-12: 2
1.2 | 2 | Fetch and display inventory | Kalder Morgan | 3 | 2026-05-09: 3
1.3 | 3 | Inventory management (admin update + validation) | Regina Cleveland | 2 | 2026-05-11: 2
1.4 | 3,5 | Automatic inventory updates after purchase | Kalder Morgan | 1 | bar: 2026-05-09
1.5 | 5 | Checkout flow (cart --> payment --> confirmation) | Phillip Cook | 4 | 2026-05-13: 2; 2026-05-14: 1; 2026-05-15: 1
1.6 | 6 | Manufacturer restock ordering + inventory update | Robert Campbell | 3 | 2026-05-12: 3
1.7 | NF | Database setup + schema design | Robert Campbell | 3 | 2026-05-08: 3
1.8 | NF | Sprint ceremonies + coordination | Phillip Cook | 2 | 2026-05-07: 2
|  | Remaining units (actual) |  | 22 | #N/A | #N/A | #N/A | 17 | 13 | 11 | 9 | 4 | 2 | 1 | 0 | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 20.4286 | 18.8571 | 17.2857 | 15.7143 | 14.1429 | 12.5714 | 11 | 9.4286 | 7.8571 | 6.2857 | 4.7143 | 3.1429 | 1.5714 | -2.2204e-15
[10 empty] | 0 | 22 | [5 empty] | 0 | 2
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Bookstore Management System (BMS)
|  | Sprint # |  | 2
|  | Start date |  | 2026-05-19
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01
2.1 | 1 | User authentication system (login, session handling, errors) | Dev Team | 3
2.2 | 4 | Shopping cart system (add/remove/update items) | Dev Team | 3
2.3 | 4,5 | Cart persistence and checkout integration | Dev Team | 4
2.4 | 7 | Sales reporting system (generate + filter reports) | Dev Team | 3
2.5 | 8 | Inventory reporting system (stock levels + status) | Dev Team | 4
2.6 | 9 | Security implementation (hashing, validation, secure APIs) | Dev Team | 2
2.7 | 9 | Protection mechanisms (rate limiting, error handling) | Dev Team | 3
2.8 | NF | Testing, demo, and documentation | Dev Team | 3
|  | Remaining units (actual) |  | 25 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 23.2143 | 21.4286 | 19.6429 | 17.8571 | 16.0714 | 14.2857 | 12.5 | 10.7143 | 8.9286 | 7.1429 | 5.3571 | 3.5714 | 1.7857 | 2.2204e-15
[10 empty] | 0 | 25 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0